## Cert
METRIO CONSTRUCTION SDN BHD | [6 empty] | CERTIFICATE OF PAYMENT | [6 empty] | Contract |  | Workdone
[11 empty] | Original | Workdone | VO List | Add | Omit | Add | Omit
LOCUS TEAM SDN BHD (315606-P) |  |  |  |  | Project Code | SB135 |  |  |  | Contract Sum |  | 242199.8 | VO.01
No. 44, Lorong Perda Utama 8, |  |  |  |  | LA no | SB135/LA01 |  |  |  | VO Addition | 0 | 0 | VO.02
Bandar Perda, |  |  |  |  | Contract Period | 5th Dec 2013 - 11th Aug 2014 |  |  |  | VO Omission | 0 | 0 | VO.03
13600 Bukit Mertajam |  |  |  |  | Original Contract Sum |  | 495133.2 |  |  | Revised Contract Sum | 0 | 242199.8 | VO.04
Tel No.: 04-539 1125 |  | Fax No. :04-539 1425 |  |  | Variation Order |  | 0 | [5 empty] | VO.05
Person incharge: | Mr Chaw Kim Hock (012-408 6255) |  |  |  | Revised Contract Sum |  | 495133.2 |  |  | Retention Sum | 0 |  | VO.06
VO.07
PROJECT TITLE: | SB135, Bukit Mertajam, Penang |  |  |  | Accm Previous Recommended |  | 8515.8 | =QS | Accumulated Site record-daywork |  |  |  | VO.08
Sub-contract for Piling Works
VO.09
Sub Contract Works |  | Lab & Mach | Building | [9 empty] | VO.10
VO.11
VO.12
Date of Valuation | 2014-01-07 | Final Account |  |  |  | % of Completion: | 1.81% |  |  | Checking | QS | Acct | VO.13
VO.14
Claim No | Value of work done | Variation Order+/- | Total work done | Retention Sum | Accm Certified todate | Previous Certified (RM) | This Materials on Site |  |  | Previous Certified |  |  | VO.15
1 | 8964 | 0 | 8964 | -448.2 | 8515.8 | -8515.8 | [6 empty] | VO.16
| 495133.2 | 0 | 495133.2 | 5% |  |  | 75% | [5 empty] | VO.17
VO.18
Amount Certified | Advance Payment | Material purchased on behalf | Kongsi Kong | Work on behalf | Permit | This Total Misc | Recommended Amount | [5 empty] | VO.19
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Checking |  |  | VO.20
[6 empty] | Due Date : | 2014-01-20 |  |  | (Previous Claims) | QS | Acct |  | 0 | 0 | 0 | 0
Prepared By, | Checked By, | Approved By, |  | Cheque No |  |  | Received By |  |  | Materials/Machinery
|  |  |  | Cheque Date | [5 empty] | Kongsi Kong |  |  |  | Site Record-Daywork
Cheque Amount
[13 empty] | Kepala |  | 0 | 100 | 0
[13 empty] | Skilled |  | 0 | 70 | 0
[13 empty] | Unskilled |  | 0 | 45 | 0
[10 empty] | Advance | [6 empty] | 0
[10 empty] | Total | 0 | 0
8515.8 | 0 | 0 | 0 | 0 | 0 | 0 | 8515.8
Amount Certified | Advance Payment | Material purchased on behalf | Kongsi Kong | Work on behalf | Permit | Total Misc | Recommended Amount
8515.8 | [6 empty] | 8515.8

## SubBQ
Project : | SB135
Subcontractor : | LOCUS TEAM SDN BHD
SubContract Works : | PILING WORKS
Re : | Subcon Claim BQ |  |  |  | j | Estimate
claim no. 01
Item | Description | Unit | Rate | Total Qty | Amount | Previous Qty | Claimed Qty | Claimed Amt
BAKAU PILES (ALL PROVISIONAL)
1 | Allow for mobilisation of machinery for Bakau Pile (A-Frame ) including moving machinery about site and demobilisation upon completion of piling works (Rate shall include for idling time) | Item | 500 | 4 | 2000
0
| Handle, pitch and drive 75mm (minimum) to 125mm diameter approved bakau piles of 5m long |  |  |  | 0 |  |  | 0
2 | Town-house (Intermediate Unit) | No. | 4.5 | 44100 | 198450 |  | 570 | 2565 | 0.85 | 484.5 |  | -2080.5
3 | Town-house (Corner Unit) | No. | 4.5 | 10999 | 49495.5 |  |  | 0 |  |  |  | 0
4 | Town-house (STAGGERED LOT) | No. | 4.5 | 12940 | 58230 |  | 315 | 1417.5 |  |  |  | -1417.5
5 | Semi-Detached | No. | 4.5 | 34200 | 153900 |  | 1107 | 4981.5 |  |  |  | -4981.5
6 | Club House | No. | 4.5 | 4075 | 18337.5 |  |  | 0 | 0.85 | 0 |  | 0
7 | TNB COMPACT SUB | No. | 4.5 | 45 | 202.5 |  |  | 0 |  |  |  | 0
8 | Refuse Chamber | No. | 4.5 | 45 | 202.5 |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 0 | 87 | 0 |  | 0
| 150mm x 150mm RC Pile for Drainage Works |  |  |  | 0 |  |  | 0 | 93 | 0 |  | 0
| Allow for the provision and mobilisation of all necessary piling equipment, plant, tools, temporary staging, working platform and ancillary equipment for installation of Hydraulic Hammer pile machine and for their transportation to site, handling assembling, moving about the site from point to point, construction of temporary hardstanding or stagings, including any excavation, earth filling, to make up level and staging for movement of plant from different level around the site, demobilisation after completion of the works and any idles time for whole duration of the works | No | 1000 | 1 | 1000 |  |  | 0 | 39 | 0 |  | 0
[5 empty] | 0 |  |  | 0 | 30 | 0 |  | 0
| Handle, transport and pitch approved precast reinforced concrete pile for driving in single or in cluster |  |  |  | 0 |  |  | 0 |  |  |  | 0
| 150mm x 150mm Initial pile 6m long | No. | included | 228 | included |  |  | included |  |  |  | #VALUE!
[5 empty] | 0 |  |  | 0 |  |  |  | 0
| 150mm x 150mm Extension pile 6m long | No. | included | 456 | included |  |  | included |  |  |  | #VALUE!
[5 empty] | 0 |  |  | 0 |  |  |  | 0
| Drive only as described single vertical 150mm x 150mm precast reinforced concrete pile | m | 2.8 | 4104 | 11491.2 |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 0 |  |  |  | 0
| 13mm V-fillet weld joint connection for 150mm x 150mm precast concrete pile between head and extension plates and including covering weld with pure bitumen | No. | 4 | 456 | 1824 |  |  | 0 | 135.69 | 132.99 | 2.7 | 132.99 | Remarks : add in the 15-18m qty in 12-15m
[5 empty] | 0 |  |  | 0 |  |  |  | 0
0
|  |  |  | Original Contract Sum: | 495133.2 |  | Total Claim Sum: | 8964 |  | 617.49 |  | #VALUE!
[7 empty] | VO | 0
[7 empty] | Total | 8964
[5 empty] | 495133.2 |  |  |  |  | -8346.51
[7 empty] | on hold for material backcharges | 0

## Misc
Misc
A. Advance Payment
Item | Date | Description | Unit | Qty | Rate | Total | Total
[6 empty] | Claim | Previous
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total |  | 0 | 0
|  |  | Total Claim - Total Previous |  |  | 0
B. Materials and Machinery Cost (Purchased/ Rental on behalf)
Item | Date | Description | Unit | Qty | Rate | Total | Total
[6 empty] | Claim | Previous
|  |  |  | Total |  | 0 | 0
|  |  | Total Claim - Total Previous |  |  | 0
C. Kongsi Kong
Item | Date | Description | Unit | Unskilled | Rate | sub-total | Skilled | Rate | sub-total | Total | Total
|  |  |  | Labour |  |  | Labour |  |  | Claim | Previous
[6 empty] | 0 |  |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0
|  | Total |  |  |  | 0 |  |  | 0 | 0 | 0
[7 empty] | Total Claim - Total Previous |  |  | 0
D. Work on behalf
Item | Date | Description | Unit | Qty | Rate | Total | Total
Previous
a. | [5 empty] | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total |  | 0 | 0
|  |  | Total Claim - Total Previous |  |  | 0
E. Permit
Item | Date | Description | Unit | Qty | Rate | Total | Total
Previous
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total |  | 0 | 0
|  |  | Total Claim - Total Previous |  |  | 0

## VO1
Project : | SB135
Subcontractor : | LOCUS TEAM SDN BHD
SubContract : | PILING WORKS
Re : | Variation Order
|  |  | MC Cost |  |  | LOCUS TEAM SDN BHD |  |  |  | This Claim (Workdone) |  | Remark
Item | Description | Unit | Total Qty | Rate | Amount | Total Qty | Rate | Amount | Qty | Rate | Amount
[13 empty] | #REF! | #REF! | #REF!
| Total Amount |  |  |  | 0 |  |  | 0 |  |  | 0
| Cost Saving (RM) | [6 empty] | 0
VO Claim Status:
Amount recommend by QS:
| Amount received: | 0
Date receive:
Remarks:
Approval by:
Ms Chew :
Mr Saw :
Mr. Loh :
Mr. Chuah :

## MOS
Project : | SB135
Subcontractor : | LOCUS TEAM SDN BHD
SubContract : | PILING WORKS
Re : | Material On Site
Item | Description | Unit | Previous Certified Qty | This Claimed Qty | Rate | Amount
|  |  |  | Total Amount |  | 0

## Record
Plot 61 + 62 | 570 | corn +int
Plot 63 + 64 | 315 | int + star
Plot 59 + 60 | 1107 | semi d
total point | 1992