## Rainwater Goods
METRIO CONSTRUCTION SDN. BHD. (810090-K)
PROPOSED CONSTRUCTION AND COMPLETION OF 26 UNITS OF 4 STOREY SHOP OFFICE AND 160 UNITS OF 21 STOREY SERVICE APARTMENT AT PHASE 8, TEMASYA GLENMARIE, SEKSYEN U1, SHAH ALAM, SELANGOR DARUL EHSAN
PROJECT: T160 - Temasya, Glenmarie
RAINWATER GOODS | [9 empty] | Michael 019-3535788 |  | Michael 019-3535788
[5 empty] | BQ |  |  | AA Budget |  | Suria Timur Metal Works S/B |  | Suria Timur Metal Works S/B
Item | Description | Unit | TO Qty | BQ Qty | Rate | Amount | Qty | Rate | Amount | Rate | Amount | Rate | Amount | Prev | Curr | To Date | % WD | Amount
[5 empty] | RM | RM |  | RM | RM | RM | RM | RM | RM |  |  |  |  | RM
RAINWATER GOODS
Upper Floor
Unplasticised rigid polyvinyl chloride pipework to BS 4576 and fittings including jointing all in accordance with the manufacturer's instruction
A | 100mm Ø waste pipe embedded in concrete slab
| Shop Block 1 | m | no info | 27 | 33 | 891 | 24 | 30 | 720 | 25.5 | 612 | 25.25 | 606 |  |  |  |  | 0
B | Extra over for bend
| Shop Block 1 | No | no info | 10 | 33 | 330 | 9 | 30 | 270 | Included | Included | Included | Included |  |  |  |  | Included
Roof
C | Approved No. 24 gauge galvanised iron sheet as described flashing 520mm girth, twice bent, one end built into joint of brickwork and other end dressed over roofing sheet
| Shop Block 1 | m | 159 | 145 | 26.95 | 3907.75 | 131 | 24.5 | 3209.5 | 26.5 | 3471.5 | 26.24 | 3437.44 |  |  |  |  | 0
| Shop Block 2 | m | 127 | 130 | 26.95 | 3503.5 | 117 | 24.5 | 2866.5 | 26.5 | 3100.5 | 26.24 | 3070.08 |  |  |  |  | 0
| Shop Block 3 | m | 127 | 130 | 26.95 | 3503.5 | 117 | 24.5 | 2866.5 | 26.5 | 3100.5 | 26.24 | 3070.08 |  |  |  |  | 0
|  | m | 413 | 405 |  |  | 365
D | Approved No22 gauge galvanised iron sheet as described gutter 1150mm girth, three times bent, one and fixed to concrete and other and dressed under roofing sheet.
| Roof Canopy ( podium ) | m |  | 9 | 100.1 | 900.9 | 8 | 91 | 728 | 72 | 576 | 71.28 | 570.24 |  |  |  |  | 0
E | Approved No22 gauge galvanised iron sheet as described gutter 830mm girth, three times bent, one and fixed to timber fascia and other and dressed under roofing sheet. |  | BQ spec = gi gutter
| Pitch roof ( apartment ) | m |  | 27 | 85.8 | 2316.6 | 24 | 78 | 1872 | 63 | 1512 | 62.37 | 1496.88 |  |  |  |  | 0
F | uPVC Gutter as per drawing BBU265/DD/RD-PS/01 |  | Dwg spec = upvc gutter
| Pitch roof ( apartment ) | m | (not in BQ) | [5 empty] | Rate Only | 45 | Rate Only | 44.55 | Rate Only |  |  |  |  | Rate Only
| 100mm dia RWDP connect from UPVC gutter to RW harvesting tank (not in BQ) | m | (not in BQ) | [5 empty] | Rate Only | 25.5 | Rate Only | 25.25 | Rate Only |  |  |  |  | Rate Only
Unplasticised rigid polyvinyl chloride pipework to BS 4576 and fittings including jointing all in accordance with the manufacturer's instruction
G | 150mm Ø rainwater downpipe fixed to wall or column
| Shop Block 1 | m | 175 | 291 | 47.3 | 13764.3 | 262 | 43 | 11266 | 43 | 11266 | 42.57 | 11153.34 |  | 262 | 262 | 100% | 11153.34
| Shop Block 2 | m | 144 | 186 | 47.3 | 8797.8 | 167 | 43 | 7181 | 43 | 7181 | 42.57 | 7109.19 | 31 | 136 | 167 | 100% | 7109.19
| Shop Block 3 | m | 144 | 186 | 47.3 | 8797.8 | 167 | 43 | 7181 | 43 | 7181 | 42.57 | 7109.19 | 59.7 | 107.3 | 167 | 100% | 7109.19
| Refuse Chamber | m | 25 | 22 | 47.3 | 1040.6 | 20 | 43 | 860 | 43 | 860 | 42.57 | 851.4 |  | 20 | 20 | 100% | 851.4
H | 150mm Ø ditto but fixed to concrete soffit
| Shop Block 1 | m | Incl | 24 | 47.3 | 1135.2 | 22 | 43 | 946 | 43 | 946 | 42.57 | 936.54 |  | 22 | 22 | 100% | 936.54 | VO
| Shop Block 2 | m | Incl | 19 | 47.3 | 898.7 | 17 | 43 | 731 | 43 | 731 | 42.57 | 723.69 |  | 17 | 17 | 100% | 723.69
| Shop Block 3 | m | Incl | 19 | 47.3 | 898.7 | 17 | 43 | 731 | 43 | 731 | 42.57 | 723.69 |  | 17 | 17 | 100% | 723.69
J | 150mm Ø ditto but embedded in concrete apron
| Refuse Chamber | m | 3 | 3 | 47.3 | 141.9 | 3 | 43 | 129 | 43 | 129 | 42.57 | 127.71 |  |  |  |  | 0
|  | m | 491 | 750 |  |  | 675
K | Extra over for bend
| Shop Block 1 | No | 54 | 57 | 33 | 1881 | 51 | 30 | 1530 | included | Included | included | Included |  |  |  |  | Included
| Shop Block 2 | No | 48 | 36 | 33 | 1188 | 32 | 30 | 960 | included | Included | included | Included |  |  |  |  | Included
| Shop Block 3 | No | 48 | 36 | 33 | 1188 | 32 | 30 | 960 | included | Included | included | Included |  |  |  |  | Included
| Refuse Chamber | No | 12 | 12 | 33 | 396 | 11 | 30 | 330 | included | Included | included | Included |  |  |  |  | Included
L | Extra over for 150mm x 150mm " T ' juction
| Shop Block 1 | No | 18 | 19 | 38.5 | 731.5 | 17 | 35 | 595 | included | Included | included | Included |  |  |  |  | Included
| Shop Block 2 | No | 16 | 12 | 38.5 | 462 | 11 | 35 | 385 | included | Included | included | Included |  |  |  |  | Included
| Shop Block 3 | No | 16 | 12 | 38.5 | 462 | 11 | 35 | 385 | included | Included | included | Included |  |  |  |  | Included
M | 150mm Ø dome outlet grating fixed on top of rainwater downpipe
| Shop Block 1 | No | 18 | 19 | 44 | 836 | 17 | 40 | 680 | 28 | 476 | 27.72 | 471.24 |  |  |  |  | 0
| Shop Block 2 | No | 16 | 12 | 44 | 528 | 11 | 40 | 440 | 28 | 308 | 27.72 | 304.92 |  |  |  |  | 0
| Shop Block 3 | No | 16 | 12 | 44 | 528 | 11 | 40 | 440 | 28 | 308 | 27.72 | 304.92 |  |  |  |  | 0
N | 100mm Ø rainwater downpipe fixed to wall or column
| Guard House | m | 3 | 3 | 28.6 | 85.8 | 3 | 26 | 78 | 25.5 | 76.5 | 25.25 | 75.75 |  |  |  |  | 0
P | 100mm Ø ditto but embedded in premix pavement
| Guard House | m | 9 | 9 | 28.6 | 257.4 | 8 | 26 | 208 | 25.5 | 204 | 25.25 | 202 |  |  |  |  | 0
Q | Extra over for bend
| Guard House | No | 1 | 1 | 33 | 33 | 1 | 30 | 30 | Included | Included | Included | Included |  |  |  |  | Included
R | 75mm Ø rainwater downpipe ( refer drawing BBU265/DD/RRD-SH/02
| Shop Block 1, 2 & 3 | m | [7 empty] | 23.5 | Rate Only | 23.27 | Rate Only |  |  |  |  | Rate Only | VO
S | Extra over for bend
| Shop Block 1, 2 & 3 | No | [7 empty] | Included | Included | Included | Included |  |  |  |  | Included
floor trap discharge at Shop corridor (detail dwg)
T | 50mm Ø waste pipe ( refer drawing BBU265/DD/RRD-SH/02
| Shop Block 1, 2 & 3 | m | [7 empty] | 30 | Rate Only | 29.7 | Rate Only |  |  |  |  | Rate Only
U | Extra over for bend |  |  | may do pipe sleeve only at site
| Shop Block 1, 2 & 3 | No | [7 empty] | Included | Included | Included | Included |  |  |  |  | Included
Approved solvent welded coloured uPVC roof drainage pipe from 'Arensi-Marley' to B.S. 4576:PT.1:1989 or other equal and approved as described :-
V | 150mm Ø rainwater downpipe fixed to wall or column
| Apartment | m | 1896 | 1896 | 47.3 | 89680.8 | 1706 | 43 | 73358 | 43 | 73358 | 42.57 | 72624.42 |  | 10 | 10 | 0.5862% | 425.7 | VO
W | 150mm Ø ditto but fixed to concrete soffit
| Apartment | m | 653 | 653 | 47.3 | 30886.9 | 588 | 43 | 25284 | 43 | 25284 | 42.57 | 25031.16 |  | 145.5 | 145.5 | 24.74% | 6193.94
|  |  | 2549 | 2549
X | Extra over for bend
| Apartment | No | 84 | 84 | 33 | 2772 | 76 | 30 | 2280 | Included | Included | Included | Included |  |  |  |  | Included
Surface Water Drainage
uPVC Class C pipe as described :-
Y | 200mmØ drain pipe fixed to concrete soffit with approved hangers | m | 330 | 343 | 67.1 | 23015.3 | 309 | 61 | 18849 | 75 | 23175 | 74.25 | 22943.25 |  | 241.65 | 241.65 | 78.2% | 17942.51
Z | 250mm Ditto | m | 111 | 109 | 83.6 | 9112.4 | 98 | 76 | 7448 | 117 | 11466 | 115.83 | 11351.34 |  | 51.9 | 51.9 | 52.96% | 6011.58
| Total Amount ( RM ) |  |  |  |  | 214872.35 |  |  | 175797.5 |  | 176053 |  | 174294.47 |  |  |  |  | 59180.77
[17 empty] | Workdone | 59180.77
VO
[17 empty] | Total | 59180.77
[17 empty] | Less 5% | -2959.0385
56221.7315
[17 empty] | Less prev payment | -29476.73
[17 empty] | Amt Certified | 26745.0015

## Summary
T160- Temasya Glenmarie
Summary RWDP- site measurement | [10 empty] | Subcon claim up to Claim No. 3
|  | Contract | Rate | Block 1 | Block 2 | Block 3 | Block 4 | total qty | total claim |  | Workdone qty | Rate | Total
A | 150mm diameter rwdp embedded in underground |  | 42.57 | 0 | 31 | 59.7 | 0 | 90.7 | 3861.099 |  | 90.7 | 42.57 | 3861.1
B | 150mm diameter rwdp fixed to wall | 2358 | 42.57 | 93.2 | 75.2 | 76.9 | 10 | 255.3 | 10868.121 |  | 255.3 | 42.57 | 10868.12
C | 100mm diameter rwdp fixed to wall |  | 25.25 | 100.4 | 62.8 | 73 | 680.7 | 916.9 | 23151.725 | VO | 548.35 | 25.25 | 13845.84
D | 75mm diameter RWDP fixed to wall | RATE ONLY | 23.27 | 76.8 | 76.8 | 76.8 | 0 | 230.4 | 5361.408 | VO | 230.4 | 23.27 | 5361.41
E | 200mm diameter drain pipe fixed to concrete soffit with approved hangers | 309 | 74.25 | 0 | 0 | 0 | 241.65 | 241.65 | 17942.5125 |  | 241.65 | 74.25 | 17942.51
F | 250mm diameter drain pipe embedded in underground | 98 | 115.83 | 14.9 | 14.5 | 22.5 | 0 | 51.9 | 6011.577 |  | 51.9 | 115.83 | 6011.58
G | 150mm diameter rwdp fixed to concrete soffit | 588 | 42.57 | 0 | 0 | 0 | 473.1 | 473.1 | 20139.867 |  | 145.5 | 42.57 | 6193.94
H | Arensi-Marley' RDP 120 fixed to wall |  | 38 | 0 | 0 | 0 | 809.9 | 809.9 | 30776.2 | VO |  | 38 | 0
[9 empty] | 118112.5095 |  |  |  | 64084.5

## site mea
T160- Temasya Glenmarie
Site Measurement
Item | Description | unit | remark | Block 1 | Block 2 | Block 3 | Apartment
A | 150mm diameter rwdp embedded in underground | m |  |  | 10 | 4.3
[5 empty] | 21 | 27.2
22.9
5.3
A |  |  |  | 0 | 31 | 59.7 | 0
B | 150mm diameter rwdp embedded in underground | m |  | 48.6 | 41 | 42.7 | 10
|  |  |  | 25.5 | 34.2 | 34.2
19.1
B |  |  |  | 93.2 | 75.2 | 76.9 | 10
C | 100mm diameter rwdp fixed to wall |  |  | 25.1 | 14.8 | 6.6 | 4.45
|  |  |  | 25.1 | 16 | 50.1 | 4.45
|  |  |  | 25.1 | 16 | 16.3 | 11.5
|  |  |  | 25.1 | 16 |  | 4.45
17
1.3
1.3
[7 empty] | 1.3 | 45.75 | G1-G1A
4.45
4.45
4.45
4.45
4.45
1.3
1.3
[7 empty] | 1.3 | 26.15 | 1A-G2
4.45
4.45
4.45
4.45
4.45
1.3
1.3
[7 empty] | 1.3 | 26.15 | 2A-1B
4.45
4.45
4.45
4.45
4.45
1.3
1.3
[7 empty] | 1.3 | 26.15 | 3A-2B
4.45
4.45
4.45
4.45
4.45
1.3
1.3
[7 empty] | 1.3 | 26.15 | 4A-3B
4.8
3.15
[7 empty] | 4.8 | 12.75 | 5A-4B
10.05
5.5
12.5
9.8
3.7
18.9
8.6
9.5
21.2
3.9
4.5
12.9
3.2
3.2
3.2
7.4
7.4
[7 empty] | 3.6 | 149.05 | Floor 6
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 7
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 8
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 9
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 10
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 11
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 12
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 13
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 14
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 15
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 16
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 17
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 18
3.75
3.75
3.75
3.75
3.75
1.2
1.2
1.2
1.2
1.2
1.2
1.2
[7 empty] | 1.2 | 28.35 | Floor 19
C |  |  |  | 100.4 | 62.8 | 73 | 680.7
D | 75mm diameter RWDP fixed to wall |  | Grd floor | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  | 1st Floor | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  | 2nd Floor | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
|  |  |  | 6.4 | 6.4 | 6.4
D |  |  |  | 76.8 | 76.8 | 76.8 | 0 |  | CHECKED
uPVC Class C pipe as described
E | 200mm diameter drain pipe fixed to concrete soffit with | [5 empty] | 4
| approved hangers | [5 empty] | 4
3.15
3.15
6.3
[7 empty] | 18.5 | 39.1 | G1-G1A
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 18.9 | 1A-G2
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 18.9 | 2A-1B
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 18.9 | 3A-2B
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 18.9 | 4A-3B
3.15
3.15
4.8
4.8
3.15
[7 empty] | 4.8 | 23.85 | 5A-4B
16.5
17.1
16.4
24.3
8.5
[7 empty] | 20.3 | 103.1 | Floor 6
E |  |  |  | 0 | 0 | 0 | 241.65
F | 250mm diameter drain pipe embedded in underground
| from shop block 3 - block 2 |  |  | 14.9 | 14.5 | 22.5
F |  |  |  | 14.9 | 14.5 | 22.5 | 0 | CHECKED
G | 150mm diameter rwdp fixed to concrete soffit | [5 empty] | 7.9
7.9
4.8
4.2
4.2
[7 empty] | 116.5 | 145.5 | Floor 6
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 7
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 8
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 9
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 10
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 11
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 12
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 13
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 14
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 15
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 16
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 17
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 18
3.15
3.15
3.15
3.15
3.15
3.15
3.15
[7 empty] | 3.15 | 25.2 | Floor 19
G |  |  |  | 0 | 0 | 0 | 473.1
H | Arensi-Marley' RDP 120 fixed to wall | [5 empty] | 4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 7
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 8
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 9
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 10
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 11
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 12
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 13
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 14
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 15
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 16
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 17
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 63.7 | Floor 18
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
4.55
[7 empty] | 4.55 | 45.5 | Floor 19
H |  |  |  | 0 | 0 | 0 | 809.9

## VO 01
Project : T160, Temasya Glenmarie
Supply and Install Rainwater Goods
|  |  | AA Budget |  |  | Suria Timur |  |  |  |  | WORKDONE
ITEM | DESCRTIPTION | UNIT | RATE(RM) | QTY | AMOUNT (RM) | RATE(RM) | QTY | AMOUNT (RM) | Prev | Curr | Todate | AMOUNT (RM) | WD%
OMISSION
Rainwater Goods
A | Unplasticised rigid polyvinyl chloride pipework to BS 4576 and fittings including jointing all in accordance with the manufacturer's instruction
150mm Ø rainwater downpipe fixed to wall or column
| Shop Block 1 | m | 47.3 | 262 | -12392.6 | 42.57 | 262 | -11153.34
| Shop Block 2 | m | 47.3 | 167 | -7899.1 | 42.57 | 167 | -7109.19
| Shop Block 3 | m | 47.3 | 167 | -7899.1 | 42.57 | 167 | -7109.19
150mm Ø ditto but fixed to concrete soffit
| Shop Block 1 | m | 47.3 | 22 | -1040.6 | 42.57 | 22 | -936.54
| Shop Block 2 | m | 47.3 | 17 | -804.1 | 42.57 | 17 | -723.69
| Shop Block 3 | m | 47.3 | 17 | -804.1 | 42.57 | 17 | -723.69
B | Approved solvent welded coloured uPVC roof drainage pipe from 'Arensi-Marley' to B.S. 4576:PT.1:1989 or other equal and approved as described :-
150mm Ø rainwater downpipe fixed to wall or column
| Apartment | m | 47.3 | 1706 | -80693.8 | 42.57 | 1706 | -72624.42 |  |  |  | 0
150mm Ø ditto but fixed to concrete soffit
| Apartment | m | 47.3 | 588 | -27812.4 | 42.57 | 588 | -25031.16 |  |  |  | 0
| SHOP / APARTMENT |  |  |  | -139345.8 |  |  | -125411.22 |  |  | 0 | 0
ADDITION
Rainwater Goods
C | Approved solvent welded coloured uPVC roof drainage pipe from 'Arensi-Marley' to B.S. 4576:PT.1:1989 or other equal and approved as described :-
120mm diameter rainwater downpipe fixed to wall
| Apartment | m |  | 809.9 | 0 | 38 | 809.9 | 30776.2
D | Unplasticised rigid polyvinyl chloride pipework to BS 4576 and fittings including jointing all in accordance with the manufacturer's instruction
100mm diameter rainwater downpipe fixed to wall or column
| Apartment | m | 28.6 | 680.7 | 19468.02 | 25.25 | 680.7 | 17187.68 |  | 0 |  | 0
150mm diameter rainwater downpipe fixed to wall or column
| Apartment | m | 47.3 | 483.1 | 22850.63 | 42.57 | 483.1 | 20565.57 |  | 0 |  | 0
E | Unplasticised rigid polyvinyl chloride pipework to BS 4576 and fittings including jointing all in accordance with the manufacturer's instruction
100mm diameter rainwater downpipe fixed to wall or column
| Shop Block 1 | m | 28.6 | 100.4 | 2871.44 | 25.25 | 100.4 | 2535.1 |  | 0 |  | 0
| Shop Block 2 | m | 28.6 | 62.8 | 1796.08 | 25.25 | 62.8 | 1585.7
| Shop Block 3 | m | 28.6 | 73 | 2087.8 | 25.25 | 73 | 1843.25
150mm diameter rainwater downpipe fixed to wall or column
| Shop Block 1 | m | 47.3 | 93.2 | 4408.36 | 42.57 | 93.2 | 3967.52 |  | 0 |  | 0
| Shop Block 2 | m | 47.3 | 106.2 | 5023.26 | 42.57 | 106.2 | 4520.93
| Shop Block 3 | m | 47.3 | 136.6 | 6461.18 | 42.57 | 136.6 | 5815.06
F | 75mm Ø Rainwater Downpipe (Refer Drawing BBU265/DD/RRD-SH/02)
| Shop Block 1, 2 & 3 | m |  | RATE ONLY |  | 23.27 | 230.4 | 5361.41 |  | 0 |  | 0
| SHOP / APARTMENT |  |  |  | 64966.77 |  |  | 94158.42 |  |  |  | 0
| TOTAL OMISSION |  |  |  | -139345.8 |  |  | -125411.22
| TOTAL ADDITION |  |  |  | 64966.77 |  |  | 94158.42
| NET OMISSION / ADDITION |  |  |  | -74379.03 |  |  | -31252.8 |  |  |  | 0
Note on D42: Ong Wan Min: No budget